Tasklist & Sprint Plan

Project Task List for AI Agent — v1.0

Phiên bản: 1.0   |   Ngày: 3/4/2026   |   Dự án: Hotel Digital Team Chatbot

# Tổng quan dự án

| Hạng mục | Chi tiết |
| --- | --- |
| Dự án | Hotel Digital Team Chatbot |
| Tổng thời gian | 16 tuần (4 sprint × 4 tuần) |
| Team | 1–2 developer + AI Agent (Claude Code) |
| Mục tiêu chi phí | < $22/tháng (200 msg/ngày) |
| Stack chính | Python FastAPI + Next.js + PostgreSQL + Claude API |

# Sprint 1 — Nền tảng (Tuần 1–4)

Mục tiêu: Hệ thống chạy được, auth hoạt động, chat cơ bản với knowledge base.

## S1-01: Setup Infrastructure

| Task ID | Mô tả | Ưu tiên | Ước tính | Giao cho |
| --- | --- | --- | --- | --- |
| S1-01-1 | Cấu hình Hetzner VPS, SSH, firewall rules | P0 | 2h | DevOps / Agent |
| S1-01-2 | Cài Docker + Docker Compose, setup volumes | P0 | 1h | DevOps / Agent |
| S1-01-3 | Tạo docker-compose.yml (postgres, nginx, app, ollama) | P0 | 3h | Dev / Agent |
| S1-01-4 | Setup PostgreSQL 16 + pgvector extension | P0 | 1h | Dev / Agent |
| S1-01-5 | Chạy schema migrations (tất cả 9 bảng) | P0 | 2h | Dev / Agent |
| S1-01-6 | Cài Ollama + pull nomic-embed-text model | P0 | 1h | Dev / Agent |
| S1-01-7 | Setup Nginx reverse proxy + Let's Encrypt SSL | P0 | 2h | DevOps / Agent |
| S1-01-8 | Tạo .env.example với tất cả biến môi trường | P1 | 1h | Dev / Agent |

## S1-02: Backend Auth

| Task ID | Mô tả | Ưu tiên | Ước tính | Giao cho |
| --- | --- | --- | --- | --- |
| S1-02-1 | Setup FastAPI project, cấu trúc thư mục, config | P0 | 2h | Dev / Agent |
| S1-02-2 | Tạo SQLAlchemy models cho 9 bảng database | P0 | 3h | Dev / Agent |
| S1-02-3 | Implement Google SSO (Authlib) | P0 | 4h | Dev / Agent |
| S1-02-4 | JWT middleware: issue, validate, refresh token | P0 | 3h | Dev / Agent |
| S1-02-5 | RBAC decorator: require_role(admin/manager/staff) | P0 | 2h | Dev / Agent |
| S1-02-6 | POST /auth/google endpoint | P0 | 1h | Dev / Agent |
| S1-02-7 | POST /auth/refresh endpoint | P0 | 1h | Dev / Agent |
| S1-02-8 | Unit tests cho auth flow | P1 | 3h | Dev / Agent |

## S1-03: Knowledge Base Core

| Task ID | Mô tả | Ưu tiên | Ước tính | Giao cho |
| --- | --- | --- | --- | --- |
| S1-03-1 | Document processor: extract text từ PDF/DOCX/XLSX | P0 | 4h | Dev / Agent |
| S1-03-2 | Chunking function (512 token, 64 overlap) | P0 | 2h | Dev / Agent |
| S1-03-3 | Embedding service gọi Ollama nomic-embed-text | P0 | 2h | Dev / Agent |
| S1-03-4 | Batch insert doc_chunks với pgvector | P0 | 2h | Dev / Agent |
| S1-03-5 | POST /knowledge/upload endpoint | P0 | 2h | Dev / Agent |
| S1-03-6 | RAG search: cosine similarity query pgvector | P0 | 3h | Dev / Agent |
| S1-03-7 | GET /knowledge/search endpoint | P0 | 1h | Dev / Agent |
| S1-03-8 | GET/PUT/DELETE /knowledge/docs endpoints | P1 | 3h | Dev / Agent |

## S1-04: Chat Core

| Task ID | Mô tả | Ưu tiên | Ước tính | Giao cho |
| --- | --- | --- | --- | --- |
| S1-04-1 | AI Service: system prompt builder với RAG context | P0 | 4h | Dev / Agent |
| S1-04-2 | Claude API wrapper với streaming (SSE) | P0 | 3h | Dev / Agent |
| S1-04-3 | Model router: Haiku vs Sonnet theo intent | P0 | 2h | Dev / Agent |
| S1-04-4 | Session management: lưu/load context_window | P0 | 2h | Dev / Agent |
| S1-04-5 | POST /chat/message endpoint (SSE streaming) | P0 | 3h | Dev / Agent |
| S1-04-6 | GET /chat/sessions và /sessions/{id}/messages | P1 | 2h | Dev / Agent |
| S1-04-7 | Response Guard: filter sensitive data trong output | P0 | 3h | Dev / Agent |
| S1-04-8 | Audit log middleware cho tất cả requests | P0 | 2h | Dev / Agent |

## S1-05: Web Chat UI

| Task ID | Mô tả | Ưu tiên | Ước tính | Giao cho |
| --- | --- | --- | --- | --- |
| S1-05-1 | Setup Next.js 14 + TypeScript + Tailwind | P0 | 1h | Frontend / Agent |
| S1-05-2 | Login page: Google SSO button | P0 | 2h | Frontend / Agent |
| S1-05-3 | Chat UI: message list, input box, send button | P0 | 4h | Frontend / Agent |
| S1-05-4 | SSE streaming render: token-by-token display | P0 | 3h | Frontend / Agent |
| S1-05-5 | Tool call indicator (hiện "Đang tra cứu lịch...") | P1 | 2h | Frontend / Agent |
| S1-05-6 | Session sidebar: danh sách cuộc trò chuyện | P1 | 3h | Frontend / Agent |
| S1-05-7 | Mobile responsive | P1 | 2h | Frontend / Agent |

# Sprint 2 — Tool Integration (Tuần 5–8)

Mục tiêu: AI có thể tạo task, set nhắc lịch, gọi Google Calendar, soạn email.

## S2-01: Task & Reminder System

| Task ID | Mô tả | Ưu tiên | Ước tính | Giao cho |
| --- | --- | --- | --- | --- |
| S2-01-1 | CRUD endpoints cho tasks (POST/GET/PATCH/DELETE) | P0 | 3h | Dev / Agent |
| S2-01-2 | CRUD endpoints cho projects | P0 | 2h | Dev / Agent |
| S2-01-3 | CRUD endpoints cho reminders | P0 | 2h | Dev / Agent |
| S2-01-4 | APScheduler: job kiểm tra reminder mỗi phút | P0 | 3h | Dev / Agent |
| S2-01-5 | Gửi reminder qua Web notification (SSE) | P0 | 2h | Dev / Agent |
| S2-01-6 | Tool definition: create_task cho Claude | P0 | 2h | Dev / Agent |
| S2-01-7 | Tool definition: set_reminder cho Claude | P0 | 2h | Dev / Agent |
| S2-01-8 | Task list UI trong frontend | P1 | 4h | Frontend / Agent |

## S2-02: Google Integration

| Task ID | Mô tả | Ưu tiên | Ước tính | Giao cho |
| --- | --- | --- | --- | --- |
| S2-02-1 | Google OAuth scopes: calendar, gmail, drive | P0 | 2h | Dev / Agent |
| S2-02-2 | Google Calendar MCP / wrapper: read/create events | P0 | 4h | Dev / Agent |
| S2-02-3 | Gmail wrapper: send email, read threads | P0 | 4h | Dev / Agent |
| S2-02-4 | Google Sheets wrapper: read/write data | P1 | 4h | Dev / Agent |
| S2-02-5 | Tool definitions cho 3 Google tools | P0 | 2h | Dev / Agent |
| S2-02-6 | Test end-to-end: "nhắc tôi họp lúc 9h mai" | P0 | 2h | Dev / Agent |
| S2-02-7 | Test: "soạn email mời họp và gửi cho team" | P0 | 2h | Dev / Agent |

## S2-03: Zalo OA Integration

| Task ID | Mô tả | Ưu tiên | Ước tính | Giao cho |
| --- | --- | --- | --- | --- |
| S2-03-1 | Đăng ký Zalo OA, lấy credentials | P0 | 1h | PM |
| S2-03-2 | POST /webhooks/zalo với HMAC verify | P0 | 3h | Dev / Agent |
| S2-03-3 | Zalo message sender: gửi text/rich message | P0 | 3h | Dev / Agent |
| S2-03-4 | Map Zalo user_id với users table | P0 | 2h | Dev / Agent |
| S2-03-5 | Test flow: nhắn Zalo → AI xử lý → reply Zalo | P0 | 2h | Dev / Agent |
| S2-03-6 | Gửi reminder qua Zalo message | P1 | 2h | Dev / Agent |

# Sprint 3 — Admin & Polish (Tuần 9–12)

Mục tiêu: Admin panel, WhatsApp, monitoring, tối ưu chi phí token.

## S3-01: Admin Panel

| Task ID | Mô tả | Ưu tiên | Ước tính | Giao cho |
| --- | --- | --- | --- | --- |
| S3-01-1 | Admin dashboard: stats tổng quan | P0 | 4h | Frontend / Agent |
| S3-01-2 | Document manager UI: upload, edit, delete docs | P0 | 5h | Frontend / Agent |
| S3-01-3 | User management: list, edit role, deactivate | P0 | 3h | Frontend / Agent |
| S3-01-4 | Audit log viewer với filter/search | P0 | 4h | Frontend / Agent |
| S3-01-5 | Token usage dashboard (cost tracking) | P1 | 3h | Frontend / Agent |
| S3-01-6 | Conversation analytics: top queries, usage by user | P1 | 4h | Frontend / Agent |

## S3-02: WhatsApp & Cost Optimization

| Task ID | Mô tả | Ưu tiên | Ước tính | Giao cho |
| --- | --- | --- | --- | --- |
| S3-02-1 | POST /webhooks/whatsapp với SHA256 verify | P1 | 3h | Dev / Agent |
| S3-02-2 | WhatsApp Business API sender | P1 | 3h | Dev / Agent |
| S3-02-3 | Prompt caching: cache system prompt (giảm 40% token) | P0 | 3h | Dev / Agent |
| S3-02-4 | Semantic cache: cache responses cho câu hỏi tương tự | P1 | 4h | Dev / Agent |
| S3-02-5 | Token budget enforcement: max 8000 tokens/request | P0 | 2h | Dev / Agent |
| S3-02-6 | Auto-summarize context khi session dài | P1 | 3h | Dev / Agent |

## S3-03: Monitoring & Reliability

| Task ID | Mô tả | Ưu tiên | Ước tính | Giao cho |
| --- | --- | --- | --- | --- |
| S3-03-1 | Setup Prometheus + Grafana (Docker) | P0 | 3h | DevOps / Agent |
| S3-03-2 | Application metrics: latency, token usage, error rate | P0 | 3h | Dev / Agent |
| S3-03-3 | UptimeRobot alert cho /health endpoint | P0 | 1h | DevOps |
| S3-03-4 | Automated daily backup script | P0 | 2h | DevOps / Agent |
| S3-03-5 | Graceful error handling khi Claude API down | P0 | 2h | Dev / Agent |
| S3-03-6 | Load test: 50 concurrent users | P1 | 3h | Dev / Agent |

# Sprint 4 — Launch & Handoff (Tuần 13–16)

Mục tiêu: Upload toàn bộ tài liệu khách sạn, train team, go live.

| Task ID | Mô tả | Ưu tiên | Ước tính | Giao cho |
| --- | --- | --- | --- | --- |
| S4-01 | Upload và verify toàn bộ tài liệu khách sạn (policies, SOPs, packages) | P0 | 8h | PM + Team |
| S4-02 | Viết system prompt chi tiết cho từng use case | P0 | 4h | PM + Dev |
| S4-03 | UAT: team test các tình huống thực tế | P0 | 8h | All |
| S4-04 | Fix bugs từ UAT | P0 | 8h | Dev / Agent |
| S4-05 | Security audit: pen test cơ bản, review logs | P0 | 4h | Dev |
| S4-06 | Viết user guide ngắn gọn cho từng role | P1 | 4h | PM / Agent |
| S4-07 | Training session cho team (1–2h) | P0 | 2h | PM |
| S4-08 | Go live: switch DNS, monitor 48h đầu | P0 | 4h | DevOps |
| S4-09 | Setup onboarding flow cho nhân viên mới | P1 | 3h | Dev + PM |
| S4-10 | Retrospective và lập kế hoạch cải tiến v1.1 | P1 | 2h | All |

# Tóm tắt timeline

| Sprint | Tuần | Milestone | Deliverable chính |
| --- | --- | --- | --- |
| Sprint 1 | 1–4 | MVP internal | Auth + Knowledge Base + Chat Web |
| Sprint 2 | 5–8 | Tool integration | Zalo + Google Calendar + Gmail + Tasks |
| Sprint 3 | 9–12 | Admin + Scale | Admin panel + WhatsApp + Monitoring |
| Sprint 4 | 13–16 | Go live | Full content + Team trained + Production |

# Hướng dẫn giao việc cho AI Agent (Claude Code)

Khi giao task cho Claude Code, cung cấp đúng context sau:

- File liên quan: chỉ rõ file nào cần đọc/sửa (ví dụ: services/rag_service.py)

- Input/output mong đợi: hàm nhận gì, trả về gì, error case nào

- Test case cụ thể: ví dụ input → expected output

- Constraint: không dùng thư viện nào, giới hạn token, version Python

- Context liên quan: copy snippet từ file khác nếu cần tham chiếu

Ví dụ prompt hiệu quả cho Claude Code:

"Implement hàm search() trong RAGService (rag_service.py).

Input: query string, top_k int, user_role string.

Dùng pgvector cosine similarity query như trong doc_chunks table schema.

Chỉ trả chunks có score > 0.7. Tham khảo schema trong database.py.

Viết unit test cho 3 cases: found, not found, access denied."